## Slide 1: High Content Data Extraction: Closure Meeting
Oleg Stroganov, PhD - Tech Lead​
Bing Zhou, PhD
Sarah Tahir - Project Manager​​
Luigi Gentile, Business Account Manager​​
April 17th, 2025

## Slide 2: Agenda
Budget/timeline updates
Project updates
Other

## Slide 3
Budget updates

## Slide 4
2024
2025
Today
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
8 days
Jul 3 - Jul 12
10 days
Jul 8 - Jul 21
183 days
Jul 22 - Apr 2
2 weeks
Apr 4 - Apr 17
183 days
Jul 22 - Apr 2
Kickoff
Create SOP
Produce 100+ Reports & QC
Feedback & Close Out
Optimizing and validating the model
Final Report
Apr 2
Timeline and Budget updates: 14-Apr-2025
Not started
In Progress
Completed
Chart: 
| Used | Remaining
Budget Overview | 0.98 | 0.02

## Slide 5
Project Overview

## Slide 6: Overall progress – original list
Manual curation of 112 genes is done;
  crawling done for 112 genes; full reports completed for 112 genes
priority 1 –
for validation
priority 2 – liver
priority 3 – other tissues
priority 4 – extra tissues
priority 5 – additional
Tissue | Gene
Liver | Phlda3
Liver | Slco2a1
Liver | Mgmt
Liver | Cpt1b
Liver | Cited4
Mammary gland | Mmp7
Tissue | Gene
Liver | Pla2g12a
Liver | Cyp1b1
Liver | Cyp4a1
Liver | Cyp3a9
Liver | Hmox1
Liver | Cyp1a2
Liver | Rbp7
Liver | Lifr
Liver | Acox1
Liver | Ehhadh
Liver | Mybl1
Liver | Mdm2
Liver | Tp53inp1
Liver | Mybl2
Liver | Vnn1
Liver | Orm1
Liver | Ctr9
Liver | Nqo1
Liver | Gclc
Liver | Ugt2b1
Liver | Hmgcs2
Liver | Ahrr
Liver | Aldh3a1
Liver | Pex11a
Liver | Nhej1
Tissue | Gene
Esophagus | Ka11
Esophagus | Fgf13
Esophagus | Pitpnm3
Esophagus | Anxa1
Esophagus | Nrg1
Esophagus | Krt17
Esophagus | Il18
Mammary gland | Mmp3
Mammary gland | Mmp13
Mammary gland | Cxcl9
Mammary gland | Cxcl12
Peripheral nerve | Il1rn
Peripheral nerve | Ccl3
Peripheral nerve | Ccl7
Peripheral nerve | Vmp1
Peripheral nerve | Gdnf
Peripheral nerve | Ccl20
Peripheral nerve | Fosl1
Peripheral nerve | Has1
Peripheral nerve | Clec4d
Prostate | Klhl15
Prostate | Shroom2
Prostate | Fam92a
Tissue | Gene
Esophagus | S100a8
Esophagus | Btg2
Esophagus | Lamc2
Liver | Ccng1
Liver | Btg2
Mammary gland | Spp1
Mammary gland | Gpnmb
Peripheral nerve | Il1b
Peripheral nerve | S100a8
Peripheral nerve | Cd44
Tissue | Gene
Liver | Cyp2b1
Liver | Atp6v1d
Liver | Aen
Liver | Bax
Liver | Lama5
Liver | Jam3
Liver | Enc1
Liver | Gria3
Liver | Tyms
Liver | Rgs3
Liver | Gas6
Liver | S100g

## Slide 7: Overall progress – extended list
priority 6 –
new genes
priority 7 – ovary
priority 8 – testis
priority 10 – Brain
priority 11 –
Lung
priority 12 –
Spleen
priority 13 –
Thymus
extra genes from different organs discussed on previous meeting
Tissue | Gene
Ovary | Anxa2
Ovary | Cdk1
Ovary | Cxcl1
Ovary | Egr2
Ovary | Fcnb
Ovary | Gpnmb
Ovary | Myc
Ovary | Olr1
Ovary | Pvr
Ovary | Runx1
Ovary | S100a4
Ovary | Serpine1
Ovary | Spp1
Ovary | Timp1
Ovary | Tnfrsf12a
Tissue | Gene
Testis | Anxa2
Testis | Cdk1
Testis | Cxcl1
Testis | Egr2
Testis | Fcnb
Testis | Gpnmb
Testis | Myc
Testis | Olr1
Testis | Pvr
Testis | Runx1
Testis | S100a4
Testis | Serpine1
Testis | Spp1
Testis | Timp1
Testis | Tnfrsf12a
priority 9 – adrenal gland
Tissue | Gene
Adrenal gland | Anxa2
Adrenal gland | Cdk1
Adrenal gland | Cxcl1
Adrenal gland | Egr2
Adrenal gland | Fcnb
Adrenal gland | Gpnmb
Adrenal gland | Myc
Adrenal gland | Olr1
Adrenal gland | Pvr
Adrenal gland | Runx1
Adrenal gland | S100a4
Adrenal gland | Serpine1
Adrenal gland | Spp1
Adrenal gland | Timp1
Adrenal gland | Tnfrsf12a
Tissue | Gene
Liver | Anxa7
Liver | Btg3
Lung | Bhlhe41
Lung | Cfi
Lung | Sgsc
Testis | Bcl2a1

## Slide 8: R shiny app
New genes added

## Slide 9: Delivered
Final project report (pdf)
SOP (pdf)
Extracted data (word docx)
  Automatically extracted data, in appendix of the report
R-shiny app (final version pending urls from NIEHS)

## Slide 10: Questions
What can we do with the poster? Would we be able to share the publication in a couple of weeks/months?
  Could we present at it other conferences?
Would you be interested in a publication for the deep research validation?

## Slide 11: Next Steps
Knowledge graph construction from literature
Exploring quality of Deep Research/Literature search
  Comparing it with manual search
Extension of gene reports
  Tissue specific curation of the genes
  New genes for exploration
Paper publication
Enabling database for easy access and visualization
  Wiki pages?
  Display and navigation
Yearly maintenance and updating of the automatic sections of reports
Validation of data produced internally by NIEHS by using or training LLM
Validation of data in the CEBS database, NTP (National Toxicology Program)

## Slide 12
Meeting Min

## Slide 13: Meeting Minutes 17-Apr-2025
Attendees: Oleg, Luigi, Scott, Kelly, Sarah
Meeting Minutes:
  Curation completed and delivered
  R-shiny app updated; ready for NIEHS
    Need the links that lead to the sites
    Rancho to send the current version
  Feedback:
    Soctt/Kelly is still reviewing the main report, have one comment
      To provide updates by April 23rd, 2025
  Questions:
    Poster: Kelly to ask around to when we may be able to present the poster
    Publication: NIEHS would not be able to provide additional budget for a manuscript
      Scott/Kelly to discuss and see what is possible for this space
Minutes added post call

## Slide 14
Older Meeting Min

## Slide 15: Meeting Minutes 20-Feb-2025
Attendees: Oleg, Laura, Scott, Kelly, Sarah
Meeting Minutes:
  Reports delivered:
    Scott reviewing the first batch (reports are consistent with what they have)
    Team will be preparing the final report as well, on the QC
    Will send an updated SOP with the final deliverables
  Deep Research- OpenAI
    Planning on including in the validation
    Relatively good; working out the kinks
    Should not be used to extract the data from sources
  Scott to be rolling this up for their gene expression studies
    Will be added to the wiki and gene clusters
  NIEHS will not be attending SOT
Minutes added post call

## Slide 16: Meeting Minutes 3-Feb-2025
Attendees: Oleg, Laura, Scott, Kelly, Sarah
Meeting Minutes:
  Phlda3 example
    Scott: terminology is important; issue of nuance
    Genotoxic vs non-genotoxic- not ideal to say both as that means nothing
      Be careful with anything related to DNA damage; look at ALT levels
  Synthesis and generalization
    Can we generalize these statements further?
      Broadens the utility of this
  Oleg to send results of LLM models on the background knowledge of LLM disease associations
    Evaluate background knowledge
  Finalizing the reports, provide first 20 by the end of this week and then send more following
  Would be great to get more feedback on the generality
    Would be great if Scott could categorize the templates
Minutes added post call

## Slide 17: Meeting Minutes 16-Jan-2025
Attendees: Oleg, Laura, Scott, Kelly, Sarah
Meeting Minutes:
  Project Updates:
    Scott and Kelly comfortable with the timeline completion of mid-February
    Scott happy with the progress so far, ready to put to the test
Minutes added post call

## Slide 18: Meeting Minutes 09-Dec-2024
Attendees: Oleg, Laura, Scott, Kelly, Sarah
Meeting Minutes:
  Validating the confidence score and how they are generated:
    Generating section 9 summaries and assigning the confidence score
    Grading system for generated statements
    Hoping to get better understanding of how this confident scores being generated; open to suggestions
      Scotts biggest concern:
        How often is CS 8 a hallucination or plausible inference
        Oleg: this is captured by "groundedness" score
        Can discuss different approaches as we proceed
  Scott: Knowledge graph, like this idea; adds value; but out of scope for current project
NIEHS holidays:
  Scott OoO: Dec 30-Jan 6th; around on Dec 23, 24; NIEHS closed Dec 25th and Jan 1st
  Rancho closed Dec 24th, 25th and Jan 1st
Minutes added post call

## Slide 19: Meeting Minutes 25-Nov-2024
Attendees: Oleg, Laura, Scott, Kelly, Nicole
Meeting Minutes:
  Gene curation plans
    May need to think about how better to assesses the quality and correlation of the quality score, once we know the results
    Scott, will be interested to see what the confidence score looks like, usual what's supported by citation is 8 or higher, 6-7 is more speculative.
      There are a few statements which are more speculative, it gives it 5-6. We can check if they are supported by context or not.
  Other topics
    Oleg: If you click on the gene it links to old wiki. Is there a std way to generate links?
      Scott: we have a download file. An example link is: https://cebs.niehs.nih.gov/cebs/get_file/accno/15938_24373/file/A2M_BoneMarrow_full.docx
      Oleg: If I substitute the name of the gene and tissue it would work?
        Scott provided link to where all links are available https://cebs-ext.niehs.nih.gov/cebs/paper/15933
          Need to click on each summary, each summary has the available links
    Oleg: Anything else to change?
      Scott: mechanism already there
    Knowledge graph construction from literature
      Scott: It would be good synthesis, is it in budget?
        Oleg: An idea of a potential future project
      Scott/Kelly: like the idea, would need to discuss internally. Need to stay in scope and budget of current SOW.
Minutes added post call

## Slide 20: Meeting Minutes 15-Nov-2024
Attendees: Oleg, Laura, Sarah, Scott, Kelly
Meeting Minutes:
  R Shiny app error:
    Schedule call: Trey, Oleg, Micheal Myers, Scott
    No NIH logins; would be better since we already have a working app; avoids some of the potential packing issues
      Rancho unable to get log in
      Trey can try to manually add user for deployment
  Can we add more genes? But will need to assess how much after completing the additional genes
    Will keep Scott posted if we have the room for more
Minutes added post call

## Slide 21: Meeting Minutes 15-Nov-2024
Attendees: Oleg, Laura, Sarah, Scott, Kelly
Meeting Minutes:
  Project Update:
    Scott to let us know if you want to switch to different tissues
      Looking at generic markers
        Leverage knowledge with broad relevance
        3 areas: necrosis, inflammation, sub proliferation
          Gpnb- generic marker for necrosis; marker of macrophages
    Single cell data:
      Reviewing public literature; from skin to spinal cord to lung
      Evaluating dose response gene expression; acting like a pathologist; seeing hepatocyte markers
Minutes added post call

## Slide 22: Meeting Minutes 28-Oct-2024
Attendees: Oleg, Laura, Sarah, Scott, Kelly
Meeting Minutes:
  Need additional genes and the priority of the genes
    Ovary (all toxicity, no mechanism)
    Testes
    Adrenal gland
    Brain
    Lung
    Spleen
    Thyroid
    Thymus
    Uterus
    To prioritize genes in one tissue and for everything else will go as far as we can with these tissues
      To work with Scott on the gene list
    To send abstract for review today, Scott to get it into the system
      Need a list of authors
    R-shiny app
      Platform: IT issues but it is moving
Minutes added post call

## Slide 23: Meeting Minutes 30-Sep-2024
Attendees: Oleg, Laura, Sarah, Scott, Kelly
Meeting Minutes:
  Ok to extend the timeline to Jan 2024
  Deliver 32 reports to Scott next week
    All the genes in wiki; Scott to review the manual reports
    To provide word docs for review
  Ka11- Scott to replace this gene
  Automation plans:
    Section 9 abstract classifications
      Would be interesting to see the features that define classification - could be worth exploring in the future
    Increase curation, decrease variability
  SOT poster
    Ok with presenting the validation; Rancho to work on the abstract
  Scott to check on their team with the R-shiny App
    Oleg: need to look into a way to update the data once the first version is deployed
Minutes added post call

## Slide 24: Meeting Minutes 16-Sep-2024
Attendees: Oleg, Laura, Sarah, Scott
Meeting Minutes:
  Standardize article selection: starting for Section 9, 10, 2 and 12
  SOT posters: to run ideas past Scott
  Understanding the evolutionary responding, and the context; don’t just discount
      Antagonistic pleiotropy
        For reproduction, advantageous to have estrogen but later in life it can lead to an increased risk of cancer
        Fibrosis and fibroblast healing can lead to cirrhosis; fibrous tissue is necessary for repair; what happens if chronic upregulation of kip1 may lead to unforeseen/wanted circumstances
      Could be advantageous early but then detrimental later
        Don’t just dismiss them in the summary
          “fire hose can save a house but also drown it”
Minutes added post call

## Slide 25: Meeting Minutes 04-Sep-2024
Attendees: Oleg, Laura, Sarah, Scott
Meeting Minutes:
  Manual curation has iterative feedback loops
    Rancho hasn’t compared with AI for this but yes it can be done with AI
  The relevance to the question is a prompt to the curators
    The greater the convergence of the prompt the better the convergence of the results
    If prompts are in greater detail; have the curators sift through and pick what's relevant
      This is what is done for section 2
    Oleg to test the variation - still a lot of filtering going on
      Curator driven section: Experience vs inexperience
        Gene in a tier; have scores for the CS
        What would be your reference study? Where would your metrics land for different genes?
          Follow up analysis is the plan
          Have a base line and will be repeating
          Same analysis and comparison
  The statements are true but not complete to some level
    The idea of a trustworthy score is loose; scores gives degree of agreement; what information is absent? What bias over information relevance?
  Great to have this baseline to compare LLM vs curators.
  Scott is glad we are doing the work; approach to be reuseable
Minutes added post call

## Slide 26: Meeting Minutes 19-Aug-2024
Attendees: Oleg, Laura, Sarah, Scott, and Kelly
Meeting Minutes:
  Curation validation
    When LLM selects references (section 2) - 66%. When references manually selected - 36% (section 9)
      Rancho to show some examples on the next meeting
  Next Meeting: Sept 4th
Minutes added post call

## Slide 27: Meeting Minutes 05-Aug-2024
Attendees: Oleg, Laura, Sarah, Scott, and Kelly
Meeting Minutes:
  Mechanistic information:
    Currently, got the association by mining through existing data
    Sometimes no ones published it yet but there is data
    Say there isn’t enough data, put those aside
      E.g. skip if we can’t find related to ER
      NIEHS will bring other genes
    Proceed where the association is clear
  Other
    Illumina Correlation Engine: process gene lists
      Would require NIEHS email address
    CTD: comparative toxinomics database- curates the literature
    If there is a way to search the literature and the supplementary data files that have some association
    Have code write the text and embed in the model
    Internal data resource that they have been mining
  Rshiny app- Scott to check in and confirm if help needed
Minutes added post call

## Slide 28: Meeting Minutes 22-Jul-2024
Attendees: Oleg, Laura, Sarah, Scott, and Kelly
Meeting Minutes:
  The already curated genes should be incorporated mechanistically:
    Cdkn1a, Srxn1, Aldh1a1, Crat (all Liver)
    Scott and Oleg to check if current summary already includes information about mechanistic pathways
  Scott to review the genes as well as give us some feedback
    Mechanistic curation will be slightly different than the toxicology; but the process shouldn’t be tweaked too much
    Ex: If you poke a liver in a rat, it gets tumors, but humans don’t; but if you poke another area in a rat, and human, the human also gets tumors
    Mechanistic and toxicology gens will be presented differently
    Activation of upstream pathway may trigger mechanistic genes, but is not necessarily related to toxicity
  R-shiny app: NIEHS working on setting up; will let us know once ready
    Oleg to send updated datasets once all is up and ready
Minutes added post call

## Slide 29: Meeting Minutes 22-Jul-2024
Attendees: Oleg, Laura, Sarah, Scott, and Kelly
Meeting Minutes:
  SOP:
    1. Tools used (eg Abstract distiller) – are they open source? internal Rancho tools; can discuss access if needed.
    NIEHS wants transparency as much as possible; find a way to be able to replicate this manually
        Trying to check citations; challenges is how you land on original data and how it becomes summarized
      Intention is that anyone can reproduce this. Scott to think about this more
    2. Dates recorded for when resources were accessed?
      Give rough dates; manual curation is done at one time and then LLM curation and qc are done on other dates; to keep track of this dates
    3. LLM – What model is being used? To write in the section/description for Abstract Distiller in current SOP. Document extraction process for sections 2, 12 & 3 is by a separate process, and will be provided as a separate document.
    4. Document specific prompt used to query LLM: to write in section/description
  To remember to make sure it is replicable
    Rancho working on replicability; are there additional standards? Scott defers to us for this but will also check internally if there’s anything else they want to see included
Minutes added post call

## Slide 30: Meeting Minutes 11-Jul-2024
Attendees: Oleg, Laura, Sarah, Scott, and Kelly
Meeting Minutes:
  Sarah to schedule biweekly- check ins
  Change to consider adding:
    Mechanism biomarkers to be included in this round of reports
      It will be clear if there are mechanistic biomarkers vs toxicity biomarkers
        Mechanistic biomarkers: genes which are overexpressed as a result of activation of upstream gene, not necessarily related to toxicity; tox biomarkers – genes which are overexpressed in response to toxicity. There is a continuum.
        Scott to indicate genes that are mechanistic biomarkers vs toxicity biomarkers in the list of genes
        To create separate sections in LLM-generated part
    Need to include the citations for the LLM generated sections
  Scott to send the list of genes
    Can expect the list in batches
    To start with 10 overstudied, 10 medium-studied and 10 less studied genes and send over by EOW
Minutes added post call

## Slide 31
Crystal Straughter
+1(860) 471 - 2082
Crystal.straughter@ranchobiosciences.com
THANK YOU
Laura Brovold
+1(760) 458 - 0692
Laura.Brovold@ranchobiosciences.com